## FYP Gantt Chart
Task | Jul 2026 | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026 | Jan 2027 | Feb 2027 | Mar 2027 | Apr 2027
Planning & Setup
FYP scope finalisation & supervisor meetings
Initial report structure setup
Literature Review
Research on cobot arms & automation
Research on displacement sensors & PdM
Research on magnetic connectors & relay systems
Write up Literature Review section
FYP Hardware — Phase 1 (Cable Automation)
Magnetic connector sourcing & procurement
PCB relay board design & fabrication
Gantry prototype frame build
Phase 1 integration & bench testing
FYP Hardware — Phase 2 (Panel Shifting)
Panel shifting mechanism design
Panel shifting build & integration
Software Development
PM Simulator (C# WinForms) continued
Software testing & debugging
System Testing & Validation
Phase 1 full system integration test
PM cycle simulation & validation
Phase 2 validation (if ready)
Report Writing
Introduction & Background
Literature Review write-up
Methodology documentation
Results & Discussion write-up
Final report compilation & polish
Submission
Presentations & Milestones
Progress Report (estimated)
Mid-Term Presentation (estimated)
Slide deck preparation
Final Presentation